## Sheet1
OUR LADY OF PEACE & BLESSED ROBERT DIBDALE, SHOTTERY STRATFORD-UPON-AVON
SCHEDULE OF WORKS OF REPAIR
based on Quinquennial 2025 report -appendix A -approx budget costings
Item | Report
Ref | Ref |  |  | BUDGET
|  | SCH A | URGENT MAINTENANCE - VOLUNTEERS | COST(£) | COMMENTS
1 | 6.2 | c) | Remove all wood/plant growth out of the rainwater guttering. Also clear away all leaves and debris from ground gullies. | 300
2 | 6.2 | g) | Replace missing feather edged boards from the south boundary fence. | 250
3 | 6.2 | h) | Trim back the shrubs growing against the west elevation and remove ivy growth. | 200
4 | 6.2 | k) | Refix loose Manhole cover to underground drainage on the South sideof the building. | 75
5 | 6.3 | f) | Redecorate the front entrance doors and glazed screen. | 1850
6 | 6.3 | g | Redecorate the kitchen walls. | 850
7 | 6.3 | j) | Redecorate all steel ( single glazed window frames | 1800
8 | 6.4 | b) Part | “Deep clean” the stained carpet to the Meeting/Family Room. | 500
9 | 6.4 | c) | Repair rotten timberwork to the external doors of the boiler house and garden store, and redecorate. | 1500
10 | 6.4 | f) | Repair damaged plaster to the wall in the children’s liturgy room | 700
11 | 6.5 | c) | Trim trees, bushes and hedging growing around the north, east and west boundaries. | 3800
11825
|  | SCH B | URGENT MAINTENANCE - CONTRACTORS /THIRD PARTY SCHEDULE
12 | 6.2 | a) | Arrange for all movement/settlement cracks to be inspected by a qualified structural engineer and carry out all recommended repair works/stabilising works.Also inspect the tree root growth at ground level adjacent to the north wall of the church. | 650
13 | 6.2 | d) | Adjust the door from the Narthex into the Church. | 200
14 | 6.2 | e) | Repair smashed window to Church (west elevation | 200
15 | 6.2 | i) | Repair fire damage to north east window opening and window. | 570
16 | 6.2 | j) | Invite L.A. Fire Officer ( or qualified Fire Consultant to visit the Church building and comment on the means of escape, fire exits, fire compartmentation, general fire safety and fire fighting equipment. | 650
17 | 6.3 | a) | Carry out careful repointing of all open mortar joints to brickwork after any loose material has been raked out. Also point up open voids in external brickwork (i.e. historic service holes . Add copings to the brick piers. | 2500
18 | 6.3 | b) | Replace damaged bricks at low level on the north, east and west side of the building. | 480
19 | 6.3 | c) | Repair/realign all rainwater gutter and downpipe connections. Refix downpipes. Avoid back falls to guttering away from outlets. | 780
20 | 6.3 | d) | Repair ground gulley to south east corner of kitchen. | 280
21 | 6.3 | h) | Repair the external plywood fascia panels and redecorate. | 3500
22 | 6.3 | l) | Seal all butt joints of aluminium cappings ( between felt and brickwork junctions . | 2800
23 | 6.3 | m) | Introduce accessible ground gulleys at the bases of the rainwater downpipes. | 2500
15110
|  | SCH C | GENERAL MAINTENANCE WITHIN 5 YEARS
24 | 6.2 | f) | Upgrade the kitchen roller shutter to the servery hatch to a half hour fire resisting shutter and also the kitchen door & frame. | 3000 | Awaiting report from Fire Inspector see 6.2j)
25 | 6.4 | b) part | Replace the carpets to the Church , sacristy, children’s liturgy room and narthex. Also“deep clean” the stained carpet to the Meeting/Family Room. | 27000
26 | 6.4 | g) | Arrange for a CCTV survey of the underground drainage system. | 2200
32200
|  | SCH D | MAINTENANCE /REPAIRS REQUIRING FURTHER CONSIDERATION
27 | 6.2 | b) | Consider insulating the church roof and external walls. | 60000
28 | 6.2 | l) | Renew central heating system within the building. | 45000 | Awaiting Boiler Inspection Report
29 | 6.3 | e) | Arrange for internal doors and frames to be upgraded to half hour fire resisting doors and frames. | 32500 | Review report from Fire Inspector see 6.2j)
30 | 6.3 | i) | Invite the Building Control Inspector to visit and comment on the existing “Accessible Toilet " | 650 | Review report from Fire Inspector see 6.2j)
31 | 6.3 | k) | Consider reducing “ cold bridge “effect due to steel beams passing through the wall structure. | 3500
32 | 6.4 | a) | Carry out re-roofing of the existing felted roofs with terne coated stainless roofing and new coping details. | 45500
33 | 6.4 | d) | Consider replacing the single glazed windows to the southelevation with double glazed windows. | 12750
34 | 6.4 | e) | Repair all cracks to plasterwork and consider full redecoration. | 15500
35 | 6.5 | a) | Remove and replace thermoplastic floor tiles to rear lobby, flower room and toilet. | 6500
36 | 6.5 | b) | Consider widening vehicle access into the church car park. | 18000
239900
|  |  | TOTAL APPROXIMATE BUDGET COSTS FROM QUINQUENNIAL INSPECTION 2025 -APPENDIX A | 299035